## Slide 1: Why are you here?
Prep for your upcoming Reflect & Reset workshop will help!
Ensure a more efficient and effective R&R session
Final KR progress is accurate and up-to-date
Learnings are identified and synthesized for review
Pilot team members share insights, contribute to next OKR cycle
1

## Slide 2: WELCOME KR CHAMPIONS AND CONGRATULATIONS!
First OKRs cycle for most of us
Most KR champions are playing this role for first time
As a KR champion you are managing work that translates to measurable positive impact on the lives of Californians!
KRs are critical areas to focus on for improvement NOW
2

## Slide 3: OKRs Cycles in 3 Steps
Step 1: Define OKRs
Step 2: Check Ins.
Step 3: Reflect & Reset.
Objectives often stay the same
Key Results mostly change
3

## Slide 4: Definition of Objectives and Key Results
OKRs: a critical thinking framework
and ongoing discipline that seeks
to ensure employees work together,
focusing effort, to make
measurable contributions
4

## Slide 5: Role of KR Champion
Update action plan + confidence bi-weekly
Communicate and reflect on progress bi-weekly using “4 check-in questions”
  Big Wins
  Blockers/barriers to success
  Learnings from working on KRs
  Next big action items
Reflect & Reset
  Reflect: Share Big Wins and Learnings
  Reset: Recommend whether to Keep, Modify, or Remove KR
5

## Slide 6: OKRs Cycle Step 3: Reflect and Reset
Pitfalls
Skipping this step entirely
Meeting gets off track and goes on forever!
Discussing only final KR progress and work completed
Solutions
Conduct the session and provide prep for KR champions!
5 min discussion per KR; classify each as Keep, Modify, or Remove
Emphasize wins and learnings, not just “final KR progress”
6

## Slide 7: OKRs Cycle Step 3: Reflect and Reset (Cont.)
Sample key result with learning that informs a draft key result for next cycle
7
Final Progress (Commit, Target, Risk) | Big Win | Learning | Keep / Modify / Remove | Optional Draft KR for next quarter
Risk. Still taking 4 months. | We defined 4 steps of hiring process Started analyzing data to see areas of improvement | Hiring managers and HR teams need more support. Found a bottleneck: application review step taking too long. | Modify | Reduce application review time for existing high-priority vacancies from 12 to 6 weeks.
KR: Reduce application hire time from 4 months to 2 months (commit = 3.5 months)
REFLECT AND RESET PROCESS

## Slide 8: Reflect and Reset Columns
OKR Title Champion End of Cycle Result Enter: "C", "T" or "R") Big Win Learning Choose "Keep, Modify, or Remove" Optional: Recommended Draft KR for Next Quarter
OKR Title Champion End of Cycle Result Enter: "C", "T" or "R") Big Win Learning Choose "Keep, Modify, or Remove" Optional: Recommended Draft KR for Next Quarter
End of Cycle Result
Enter: “C”, “T” or “R”)
Big Win
Learning
Optional: Recommended Draft KR for Next Quarter
8
 | OKR Title | Champion
Obj 1 |  | 
KR 1.1 |  | 
KR 1.2 |  | 
KR 1.3 |  | 
Obj 2 |  | 
KR 2.1 |  | 
KR 2.2 |  | 
KR 2.3 |  | 
End of Cycle Result Enter: “C”, “T” or “R”) | Big Win | Learning | Optional: Recommended Draft KR for Next Quarter
STEP 1: OKRs through Aug 31
STEP 3: REFLECT AND RESET SECTION (TO BE COMPLETED BEFORE SEPTEMBER WORKSHOP)

## Slide 9: Exercise: Observe Prep for Reflect & Reset Workshop
This is what KR champions complete in OKR Tracker as prep for September workshops
Final Progress (Commit, Target, Risk) | Big Win | Learning | Keep / Modify / Remove | Optional Draft KR for next quarter (or new Objective)
KR:
Champion:
9

## Slide 10: Next Steps
Preparing for your Reflect & Reset Workshop
10

## Slide 11: Q&A

## Slide 12: APPENDIX

## Slide 13: OKRs Cycle Step 1: Define OKRs
Pitfalls
Defining too many OKRs
Writing key results as a list of tasks, measuring output not outcomes
Failing to define why the objective is important now
Solutions
Focus on 1-2 (at most 3) objectives per team
Distinguish between key results, success metrics, and tasks
Align on why each objective is important prior to drafting key results
13
Created by Ben Lamorte

## Slide 14: OKRs are not everything! Key Results, Success Metrics, Just Do Its
    OKRs
    What: The things we want to focus effort on in near term to make measurable improvements
    Increase weekly active users of program ABC from 100 to 200
    Not OKRs
    Success Metrics
    What: Things we need to continue tracking, but are not focused on improving right now
    Maintain service level at 99.99%
    2. JUST DO ITs!
    What: Things we need to do that are important but are not measured as an OKR. May be a compliance activity or a project that impacts a success metric and/or KR.
    Examples: Update security software, complete the audit, interview people
Key Takeaways
Do not map all work into OKRs!
Just because it is measured, does not make it a KR.
14
Created by Ben Lamorte

## Slide 15: OKRs Cycle Step 2 - Check Ins Gerri working with pilot teams to complete now
Pitfalls
Zero OKRs review means “Set-it-and-forget-it”
Additional “OKR-specific” meetings/processes
Lack of clarity about who’s accountable for updating key results
Solutions
Integrate OKRs into existing team meetings
Update confidence on each key result, regularly during quarter
KR Champions update progress and serve as point person for each KR
15
Created by Ben Lamorte

## Slide 16: KR Champion: Check-In Template with “the 4 questions”
Box 1—Progress & Learnings Big “Wins" in last two weeks Learnings from working on KRs | Box 2—Confidence Is the KR on track to make the Commit, Target or it is at Risk?
Box 3—Blockers/barriers to success | Box 4—Next big action items
16
Created by Ben Lamorte